## Summary
FTF Status Flagged Orders — As of May 6, 2026
Severity | Count | Threshold | Description
CRITICAL | 18 | ≥ 500 hours in active status | Orders stuck 20+ days — immediate attention required
HIGH | 10 | 300–499 hours in active status | Orders stuck 12–20 days — escalation needed
WARN | 2 | 240–299 hours in active status | Orders stuck 10–12 days — monitor closely
TOTAL | 30 | ≥ 240 hours | All flagged active orders (excl. On Hold)
Top Issues by Status: |  |  | Crew Assignments with CRITICAL flags:
Quote | 15 |  | Unassigned | 9
Drafting Queue | 8 |  | Ricardot | 2
Assigned | 5 |  | Ex_field | 1
Drafting | 2 |  | Elenam | 1
|  |  | Alije | 1
|  |  | Johnv | 1
|  |  | Andrewy | 1
|  |  | Raul | 1
|  |  | Clollis | 1

## All Flagged Orders
FTF Flagged Orders — As of May 6, 2026 (Non-On-Hold orders stuck ≥240h)
# | Severity | Order Number | Address | County | Crew | Status | In Status Since | Hrs in Status | Days in Status | Total Age (hrs) | Total Age (days)
1 | CRITICAL | 1000257291 | 9025 SE BRIDGE RD | Martin County | Ex_field | Assigned | 2026-03-06 22:45 | 1453 | 60.5 | 11077 | 461.5
2 | CRITICAL | 1000280003 | 6805 LYLA LANE | Sarasota County | Unassigned | Quote | 2026-03-10 13:51 | 1366 | 56.9 | 1387 | 57.8
3 | CRITICAL | 1000280099 | 5550 STEAMBOAT RD | St. Johns County | Unassigned | Quote | 2026-03-10 20:58 | 1359 | 56.6 | 1363 | 56.8
4 | CRITICAL | 1000279412 | 4384 KEMPSON LN | Charlotte County | Ricardot | Drafting Queue | 2026-03-12 22:04 | 1310 | 54.6 | 1651 | 68.8
5 | CRITICAL | 1000270268 | 19366 NW 294TH ST | Okeechobee County | Elenam | Drafting Queue | 2026-03-15 19:12 | 1241 | 51.7 | 6170 | 257.1
6 | CRITICAL | 1000280456 | 5465 SE FOREST GLADE TRAIL | Martin County | Unassigned | Quote | 2026-03-17 17:02 | 1195 | 49.8 | 1199 | 50
7 | CRITICAL | 1000280814 | 10911 BROWN PELICAN CIR | Lee County | Unassigned | Quote | 2026-03-24 15:24 | 1028 | 42.8 | 1051 | 43.8
8 | CRITICAL | 1000280896 | 8608 N 13TH ST | Hillsborough County | Unassigned | Quote | 2026-03-24 19:51 | 1024 | 42.7 | 1028 | 42.8
9 | CRITICAL | 1000281059 | 349 NW 46TH ST | Miami-Dade County | Unassigned | Quote | 2026-03-27 13:32 | 958 | 39.9 | 962 | 40.1
10 | CRITICAL | 1000281365 | 3219 WHITE BLVD | Collier County | Unassigned | Quote | 2026-04-01 21:26 | 830 | 34.6 | 835 | 34.8
11 | CRITICAL | 1000281408 | 3446 ANGLIN DR | Sarasota County | Unassigned | Quote | 2026-04-02 17:31 | 810 | 33.8 | 814 | 33.9
12 | CRITICAL | 1000269556 | 662 FLAMINGO RD | Sarasota County | Ricardot | Drafting Queue | 2026-04-03 16:01 | 788 | 32.8 | 6435 | 268.1
13 | CRITICAL | 1000266714 | 4345 6TH AVE NE | Collier County | Alije | Drafting Queue | 2026-04-04 20:50 | 759 | 31.6 | 7584 | 316
14 | CRITICAL | 1000281604 | 8667 SE 157TH PL | Marion County | Unassigned | Quote | 2026-04-07 15:54 | 692 | 28.8 | 696 | 29
15 | CRITICAL | 1000273780 | 2922 SW 68TH LN | Alachua County | Johnv | Drafting Queue | 2026-04-10 16:19 | 620 | 25.8 | 4515 | 188.1
16 | CRITICAL | 1000275475 | 5729 SW 60TH AVE | Miami-Dade County | Andrewy | Drafting Queue | 2026-04-10 19:43 | 616 | 25.7 | 3649 | 152
17 | CRITICAL | 1000264423 | 1606 DESOTO AVENUE | Lee County | Raul | Drafting Queue | 2026-04-14 17:04 | 523 | 21.8 | 8615 | 359
18 | CRITICAL | 1000281328 | 1462 NW 2ND AVE | Miami-Dade County | Clollis | Assigned | 2026-04-14 20:13 | 520 | 21.7 | 838 | 34.9
19 | HIGH | 1000282132 | 12075 NW 11TH ST | Broward County | Unassigned | Quote | 2026-04-15 20:20 | 496 | 20.7 | 500 | 20.8
20 | HIGH | 1000282154 | 4049 SE 6TH WAY | Sumter County | Unassigned | Quote | 2026-04-16 17:45 | 474 | 19.8 | 481 | 20
21 | HIGH | 1000270875 | 605 COUNTY ROAD 217 | Clay County | Joseph | Drafting Queue | 2026-04-16 20:04 | 472 | 19.7 | 5879 | 245
22 | HIGH | 1000280435 | 408 JACKSON DR | Sarasota County | Unassigned | Drafting | 2026-04-17 16:30 | 451 | 18.8 | 1202 | 50.1
23 | HIGH | 1000282274 | 822 WOODLAWN ST | Pinellas County | Unassigned | Quote | 2026-04-17 18:16 | 450 | 18.8 | 454 | 18.9
24 | HIGH | 1000282398 | Lot 1890 Louise Street | Palm Beach County | Unassigned | Quote | 2026-04-21 12:55 | 359 | 15 | 378 | 15.8
25 | HIGH | 1000281850 | E MANASOTA BEACH RD | Sarasota County | Clollis | Assigned | 2026-04-21 21:31 | 350 | 14.6 | 623 | 26
26 | HIGH | 1000282084 | 5800 S MILITARY TRAIL | Palm Beach County | Chauncey_w | Assigned | 2026-04-22 00:53 | 347 | 14.5 | 506 | 21.1
27 | HIGH | 1000282493 | 39751 ANCHOR AVE | Lake County | Unassigned | Quote | 2026-04-22 14:48 | 333 | 13.9 | 338 | 14.1
28 | HIGH | 1000282536 | 1101 N FEDERAL HWY 1 | Palm Beach County | Unassigned | Quote | 2026-04-23 21:40 | 302 | 12.6 | 333 | 13.9
29 | WARN | 1000282550 | 210 OCEAN TERRACE | Palm Beach County | Ex_field | Assigned | 2026-04-24 13:01 | 287 | 12 | 331 | 13.8
30 | WARN | 1000282041 | 18910 SW 32ND CT | Broward County | Luis_p | Drafting | 2026-04-24 16:54 | 283 | 11.8 | 525 | 21.9

## CRITICAL (500h+)
CRITICAL Flagged Orders — 18 orders stuck 500+ hours as of May 6, 2026
# | Severity | Order Number | Address | County | Crew | Status | In Status Since | Hrs in Status | Days in Status | Total Age (hrs) | Total Age (days)
1 | CRITICAL | 1000257291 | 9025 SE BRIDGE RD | Martin County | Ex_field | Assigned | 2026-03-06 22:45 | 1453 | 60.5 | 11077 | 461.5
2 | CRITICAL | 1000280003 | 6805 LYLA LANE | Sarasota County | Unassigned | Quote | 2026-03-10 13:51 | 1366 | 56.9 | 1387 | 57.8
3 | CRITICAL | 1000280099 | 5550 STEAMBOAT RD | St. Johns County | Unassigned | Quote | 2026-03-10 20:58 | 1359 | 56.6 | 1363 | 56.8
4 | CRITICAL | 1000279412 | 4384 KEMPSON LN | Charlotte County | Ricardot | Drafting Queue | 2026-03-12 22:04 | 1310 | 54.6 | 1651 | 68.8
5 | CRITICAL | 1000270268 | 19366 NW 294TH ST | Okeechobee County | Elenam | Drafting Queue | 2026-03-15 19:12 | 1241 | 51.7 | 6170 | 257.1
6 | CRITICAL | 1000280456 | 5465 SE FOREST GLADE TRAIL | Martin County | Unassigned | Quote | 2026-03-17 17:02 | 1195 | 49.8 | 1199 | 50
7 | CRITICAL | 1000280814 | 10911 BROWN PELICAN CIR | Lee County | Unassigned | Quote | 2026-03-24 15:24 | 1028 | 42.8 | 1051 | 43.8
8 | CRITICAL | 1000280896 | 8608 N 13TH ST | Hillsborough County | Unassigned | Quote | 2026-03-24 19:51 | 1024 | 42.7 | 1028 | 42.8
9 | CRITICAL | 1000281059 | 349 NW 46TH ST | Miami-Dade County | Unassigned | Quote | 2026-03-27 13:32 | 958 | 39.9 | 962 | 40.1
10 | CRITICAL | 1000281365 | 3219 WHITE BLVD | Collier County | Unassigned | Quote | 2026-04-01 21:26 | 830 | 34.6 | 835 | 34.8
11 | CRITICAL | 1000281408 | 3446 ANGLIN DR | Sarasota County | Unassigned | Quote | 2026-04-02 17:31 | 810 | 33.8 | 814 | 33.9
12 | CRITICAL | 1000269556 | 662 FLAMINGO RD | Sarasota County | Ricardot | Drafting Queue | 2026-04-03 16:01 | 788 | 32.8 | 6435 | 268.1
13 | CRITICAL | 1000266714 | 4345 6TH AVE NE | Collier County | Alije | Drafting Queue | 2026-04-04 20:50 | 759 | 31.6 | 7584 | 316
14 | CRITICAL | 1000281604 | 8667 SE 157TH PL | Marion County | Unassigned | Quote | 2026-04-07 15:54 | 692 | 28.8 | 696 | 29
15 | CRITICAL | 1000273780 | 2922 SW 68TH LN | Alachua County | Johnv | Drafting Queue | 2026-04-10 16:19 | 620 | 25.8 | 4515 | 188.1
16 | CRITICAL | 1000275475 | 5729 SW 60TH AVE | Miami-Dade County | Andrewy | Drafting Queue | 2026-04-10 19:43 | 616 | 25.7 | 3649 | 152
17 | CRITICAL | 1000264423 | 1606 DESOTO AVENUE | Lee County | Raul | Drafting Queue | 2026-04-14 17:04 | 523 | 21.8 | 8615 | 359
18 | CRITICAL | 1000281328 | 1462 NW 2ND AVE | Miami-Dade County | Clollis | Assigned | 2026-04-14 20:13 | 520 | 21.7 | 838 | 34.9

## Quote Status Issues
Quote Status — 15 orders stuck without being assigned (as of May 6, 2026)
NOTE: Quote orders are awaiting pricing/assignment. These have not been assigned to any crew. Average time stuck: 778h
# | Severity | Order Number | Address | County | Crew | Status | In Status Since | Hrs in Status | Days in Status | Total Age (hrs) | Total Age (days)
1 | CRITICAL | 1000280003 | 6805 LYLA LANE | Sarasota County | Unassigned | Quote | 2026-03-10 13:51 | 1366 | 56.9 | 1387 | 57.8
2 | CRITICAL | 1000280099 | 5550 STEAMBOAT RD | St. Johns County | Unassigned | Quote | 2026-03-10 20:58 | 1359 | 56.6 | 1363 | 56.8
3 | CRITICAL | 1000280456 | 5465 SE FOREST GLADE TRAIL | Martin County | Unassigned | Quote | 2026-03-17 17:02 | 1195 | 49.8 | 1199 | 50
4 | CRITICAL | 1000280814 | 10911 BROWN PELICAN CIR | Lee County | Unassigned | Quote | 2026-03-24 15:24 | 1028 | 42.8 | 1051 | 43.8
5 | CRITICAL | 1000280896 | 8608 N 13TH ST | Hillsborough County | Unassigned | Quote | 2026-03-24 19:51 | 1024 | 42.7 | 1028 | 42.8
6 | CRITICAL | 1000281059 | 349 NW 46TH ST | Miami-Dade County | Unassigned | Quote | 2026-03-27 13:32 | 958 | 39.9 | 962 | 40.1
7 | CRITICAL | 1000281365 | 3219 WHITE BLVD | Collier County | Unassigned | Quote | 2026-04-01 21:26 | 830 | 34.6 | 835 | 34.8
8 | CRITICAL | 1000281408 | 3446 ANGLIN DR | Sarasota County | Unassigned | Quote | 2026-04-02 17:31 | 810 | 33.8 | 814 | 33.9
9 | CRITICAL | 1000281604 | 8667 SE 157TH PL | Marion County | Unassigned | Quote | 2026-04-07 15:54 | 692 | 28.8 | 696 | 29
10 | HIGH | 1000282132 | 12075 NW 11TH ST | Broward County | Unassigned | Quote | 2026-04-15 20:20 | 496 | 20.7 | 500 | 20.8
11 | HIGH | 1000282154 | 4049 SE 6TH WAY | Sumter County | Unassigned | Quote | 2026-04-16 17:45 | 474 | 19.8 | 481 | 20
12 | HIGH | 1000282274 | 822 WOODLAWN ST | Pinellas County | Unassigned | Quote | 2026-04-17 18:16 | 450 | 18.8 | 454 | 18.9
13 | HIGH | 1000282398 | Lot 1890 Louise Street | Palm Beach County | Unassigned | Quote | 2026-04-21 12:55 | 359 | 15 | 378 | 15.8
14 | HIGH | 1000282493 | 39751 ANCHOR AVE | Lake County | Unassigned | Quote | 2026-04-22 14:48 | 333 | 13.9 | 338 | 14.1
15 | HIGH | 1000282536 | 1101 N FEDERAL HWY 1 | Palm Beach County | Unassigned | Quote | 2026-04-23 21:40 | 302 | 12.6 | 333 | 13.9