## HEADLINE NUMBERS
NexGen Field to Finish — Year-Over-Year Comparison ¦ January – April
How are we doing in 2026 vs. the same four months in 2025?
2026 data is year-to-date as of May 5, 2026. April 2026 orders may still be in progress.
Metric | 2025 (Jan-Apr) | 2026 (Jan-Apr) | Change | Trend | Grade | What It Means
Total Orders | 7,539 | 6,397 | -1,142 | DOWN 15% | C+ | Volume dropped by 1,142 orders. Fewer jobs coming in vs same period last year.
Orders Completed | 5,239 | 4,022 | -1,217 | DOWN 23% | C | Partly because many 2026 orders are still in pipeline. Watch end-of-year final count.
Completion Rate | 69.5% | 62.9% | -6.6% | DOWN 6.6 pts | C | 2026 completing fewer orders per dollar of intake. Go-backs are delaying completions.
Go-Backs (count) | 410 | 991 | +581 | UP +141% | F | GO-BACKS NEARLY TRIPLED. 581 extra redos in the same 4-month window. This is the #1 crisis.
Go-Back Rate | 5.4% | 15.5% | +10.1 pts | TRIPLED | F | Was 1-in-18 jobs. Now 1-in-6.5 jobs. Every crew must know this number and fix it.
Cancellations | 2,191 | 1,682 | -509 | DOWN (GOOD) | B | 509 fewer cancellations — the one bright spot in 2026. Positive trend to maintain.
Cancel Rate | 29.1% | 26.3% | -2.8 pts | IMPROVED | B | Cancel rate fell from 29.1% to 26.3%. Good direction. Keep investigating the cause.
BOTTOM LINE: The go-back rate TRIPLED (5.4% to 15.5%) in 2026. That means crews are re-doing 1 in every 6.5 jobs — costing fuel, time, and client trust. Fix the go-back explosion first. Everything else is secondary.

## MONTHLY TRENDS
Month-by-Month Comparison ¦ January – April ¦ 2025 vs 2026
Each month compared side-by-side. Look for where 2026 falls behind.
Month | 2025 Orders | 2026 Orders | Order Change | 2025 Comp% | 2026 Comp% | Comp% Change | 2025 GB% | 2026 GB% | GB% Change | Monthly Verdict
January | 1825 | 1323 | -502 | 68.4% | 66.6% | -1.8% | 5.3% | 22.4% | +17.1% | GO-BACKS CRISIS
February | 1833 | 1486 | -347 | 67.3% | 68.6% | +1.3% | 4.3% | 25.4% | +21.1% | GO-BACKS CRISIS
March | 1995 | 1770 | -225 | 71.8% | 65.9% | -5.9% | 4.6% | 11.4% | +6.8% | GO-BACKS UP
April | 1886 | 1818 | -68 | 70.3% | 52.5% | -17.8% | 7.6% | 6.4% | -1.2% | MIXED
TOTAL | 7,539 | 6,397 | -1,142 | 69.5% | 62.9% | -6.6% | 5.4% | 15.5% | +10.1% | SEE HEADLINE
Month | 2025 Orders | 2026 Orders |  | Month | 2025 GB% | 2026 GB% |  | Month | 2025 Comp% | 2026 Comp%
January | 1825 | 1323 |  | January | 5.3 | 22.4 |  | January | 68.4 | 66.6
February | 1833 | 1486 |  | February | 4.3 | 25.4 |  | February | 67.3 | 68.6
March | 1995 | 1770 |  | March | 4.6 | 11.4 |  | March | 71.8 | 65.9
April | 1886 | 1818 |  | April | 7.6 | 6.4 |  | April | 70.3 | 52.5

## CREW SCORECARDS
Crew Performance — Go-Back Rate Comparison ¦ Jan–Apr 2025 vs 2026
LOWER go-back % = fewer re-dos = better quality. Sorted worst decline first.
RED rows = getting worse ¦ GREEN rows = improving ¦ Target: under 10% go-back
Crew Name | 2025 Jobs | 2025 GB% | 2026 Jobs | 2026 GB% | Change in GB% | Status | 2025 Rating | 2026 Rating
Rc | 133 | 3.8% | 114 | 45.6% | +41.8% | BIG DROP ↓↓ | STAR | CRITICAL
Choppa | 235 | 11.1% | 76 | 51.3% | +40.2% | BIG DROP ↓↓ | GOOD | CRITICAL
Byron | 266 | 5.3% | 222 | 42.3% | +37.0% | BIG DROP ↓↓ | GREAT | CRITICAL
Tejada | 87 | 4.6% | 145 | 35.2% | +30.6% | BIG DROP ↓↓ | STAR | CRITICAL
Richardp | 145 | 5.5% | 212 | 34.9% | +29.4% | BIG DROP ↓↓ | GREAT | CRITICAL
Ivan | 218 | 5.5% | 357 | 31.9% | +26.4% | BIG DROP ↓↓ | GREAT | CRITICAL
Mabel | 132 | 7.6% | 105 | 28.6% | +21.0% | DECLINING ↓ | GREAT | CRITICAL
Elio | 92 | 3.3% | 59 | 20.3% | +17.0% | DECLINING ↓ | STAR | CONCERN
Manuel | 224 | 11.6% | 226 | 27.9% | +16.3% | DECLINING ↓ | GOOD | CRITICAL
Alije | 707 | 6.9% | 619 | 19.1% | +12.2% | DECLINING ↓ | GREAT | CONCERN
Andrewy | 125 | 14.4% | 136 | 26.5% | +12.1% | DECLINING ↓ | OK | CRITICAL
Juans | 306 | 9.5% | 217 | 21.2% | +11.7% | WATCH ↓ | GOOD | CONCERN
Chauncey_w | 206 | 14.1% | 133 | 24.8% | +10.7% | WATCH ↓ | OK | CONCERN
Raul | 387 | 8.8% | 224 | 18.8% | +10.0% | WATCH ↓ | GREAT | CONCERN
Elenam | 106 | 9.4% | 231 | 18.2% | +8.8% | WATCH ↓ | GOOD | CONCERN
Ricardot | 363 | 7.4% | 358 | 15.1% | +7.7% | WATCH ↓ | GREAT | OK
Rose | 421 | 2.9% | 120 | 9.2% | +6.3% | WATCH ↓ | STAR | GOOD
Davidy | 78 | 0.0% | 68 | 5.9% | +5.9% | WATCH ↓ | PERFECT | GREAT
Jonp | 250 | 11.6% | 115 | 14.8% | +3.2% | WATCH ↓ | GOOD | OK
Ray | 236 | 4.7% | 169 | 7.7% | +3.0% | STABLE → | STAR | GREAT
Anthonya | 78 | 2.6% | 37 | 2.7% | +0.1% | STABLE → | STAR | STAR
Joseph | 79 | 2.5% | 56 | 1.8% | -0.7% | STABLE → | STAR | STAR
Diegor | 155 | 5.8% | 131 | 4.6% | -1.2% | STABLE → | GREAT | STAR
Johnv | 131 | 10.7% | 88 | 3.4% | -7.3% | IMPROVING ↑ | GOOD | STAR
NEW IN 2026 (no 2025 data): Brian_g — 0.0% GB (7 jobs) ¦ Luis_p — 0.0% GB (14 jobs) — Both new, both off to a great start.
Crew | 2025 GB% | 2026 GB%
Rc | 3.8 | 45.6
Choppa | 11.1 | 51.3
Byron | 5.3 | 42.3
Tejada | 4.6 | 35.2
Richardp | 5.5 | 34.9
Ivan | 5.5 | 31.9
Mabel | 7.6 | 28.6
Elio | 3.3 | 20.3
Manuel | 11.6 | 27.9
Alije | 6.9 | 19.1
Andrewy | 14.4 | 26.5
Juans | 9.5 | 21.2
Chauncey_w | 14.1 | 24.8
Raul | 8.8 | 18.8

## DRAFTER SCORECARDS
Drafter Performance Comparison ¦ January–April 2025 vs 2026
Drafters who appear in both years — go-back rate is the key quality measure.
Drafter | 2025 Drafts | 2025 GB% | 2026 Drafts | 2026 GB% | Change in GB% | Status | Key Finding
Oleg | 4966 | 5.9% | 4083 | 23.2% | +17.3% | BIG DROP ↓↓ | CRISIS: Handles 65% of ALL drafting. Go-back rate quadrupled (5.9% → 23.2%). Senior review needed immediately. Root cause unknown.
Caitlyn | 27 | 22.2% | 17 | 70.6% | +48.4% | CRISIS ↓↓↓ | STOP assignments. Was 22% in 2025 — already bad. Now 70.6%. 7 in 10 drafts returned. Requires full senior sign-off on every draft.
Glenn | 138 | 18.1% | 12 | 16.7% | -1.4% | STABLE → | Slight improvement (18.1% → 16.7%). Low 2026 volume — may have shifted to other duties. Still above 10% target.
Jon_w | 2 | 50.0% | 37 | 43.2% | -6.8% | IMPROVING ↑ | 2025 data is only 2 drafts — not comparable. 2026 rate of 43.2% on 37 drafts is unacceptable. Needs senior oversight.
DRAFTERS ACTIVE IN 2025 (Jan-Apr) BUT NOT IN 2026:
Anogueira | 193 drafts | 37.3% GB | (not in 2026) | — | N/A | DEPARTED | Not active 2026 (Jan-Apr). Was a quality drag — neutral to positive that workload shifted.
Fred_draft | 23 drafts | 30.4% GB | (not in 2026) | — | N/A | DEPARTED | Appears removed after 2025 full-year review. Correct decision.
Kevin | 26 drafts | 15.4% GB | (not in 2026) | — | N/A | DEPARTED | Not found in 2026 data. Availability issue or redeployment.
Sandra | 30 drafts | 6.7% GB | (not in 2026) | — | N/A | DEPARTED | Strong drafter — NOT in 2026 Jan-Apr. Recommend re-engaging if available.
NEW DRAFTERS IN 2026 (no 2025 comparison): Alex_m — 0.0% (7 drafts) ¦ Amann — 0.0% (5) ¦ Alma_t — 28.6% (14) ¦ Mark_e — 60.0% (5 — too small to judge)
Drafter | 2025 GB% | 2026 GB%
Oleg | 5.9 | 23.2
Caitlyn | 22.2 | 70.6
Glenn | 18.1 | 16.7
Jon_w | 50 | 43.2

## COORDINATOR REPORT
Survey Coordinator Performance ¦ January–April 2026
NOTE: Coordinator tracking field (survey_coordinator) was barely used in 2025. Only 6 records vs 145 in 2026.
2026 coordinators with meaningful tracked activity:
Coordinator | Orders Managed | Completed | Cancelled | Go-Backs | Comp Rate | Assessment
Marcos | 90 | 89 | 0 | 9 | 98.9% | EXCELLENT — Near-perfect completion, zero cancellations on 90 orders. Use his process as the company standard.
Jon_w | 47 | 44 | 2 | 5 | 93.6% | GOOD — Strong completion on 47 managed orders. 5 go-backs is within target. Keep monitoring.
ACTION REQUIRED: Make survey_coordinator a required field for all new orders immediately. Without it, we cannot measure coordinator accountability. Marcos's 98.9% completion rate is the benchmark every coordinator should be held to.
CONTEXT: In 2025 Jan-Apr there were only 6 total coordinator-assigned records vs 7,539 total orders. In 2026 there are 145 records vs 6,397 orders. Still less than 3% coverage. This data gap means coordinator comparison is not yet possible — but 2026 is heading in the right direction.

## WHO TO WATCH
WHO TO WATCH — Plain-English Summary ¦ Jan–Apr 2025 vs 2026
Named list of who improved, who declined, and what to do about it.
CREW MEMBERS — PERFORMANCE GETTING WORSE (Go-Back Rate Rose Significantly)
Crew | 2025 GB% | 2026 GB% | How Bad | Action Required
Rc | 3.8% | 45.6% | CRITICAL | From STAR to CRISIS. 45.6% in 2026. Audit all recent work. Personal coaching session within 3 days.
Choppa | 11.1% | 51.3% | CRITICAL | STOP solo complex jobs. 51% means 1 in 2 jobs wrong. Supervisor must ride along this week.
Byron | 5.3% | 42.3% | CRITICAL | 5.3% → 42.3%. Something changed. Ask crew what's different. Could be equipment, area, or personal issue.
Tejada | 4.6% | 35.2% | CRITICAL | Was a top crew in 2025. Now 35.2%. Has taken on more volume — workload overload may be the cause.
Richardp | 5.5% | 34.9% | SERIOUS | 34.9% on 212 jobs = 74 wrong jobs. Add supervisor pre-check before submission.
Ivan | 5.5% | 31.9% | SERIOUS | 31.9% on 357 jobs = 114 wrong jobs. High volume + high error = biggest absolute impact on operations.
Mabel | 7.6% | 28.6% | SERIOUS | 7.6% → 28.6%. Nearly quadrupled. Check if equipment changed or job complexity increased.
Elio | 3.3% | 20.3% | SERIOUS | 3.3% → 20.3%. Was excellent, now a concern. Check if new assignments types are different.
Manuel | 11.6% | 27.9% | SERIOUS | 11.6% → 27.9%. 63 go-backs on 226 jobs. Targeted coaching on most common error types.
Alije | 6.9% | 19.1% | CONCERN | 6.9% → 19.1%. High-volume crew with a serious slip. Needs attention before errors compound.
Andrewy | 14.4% | 26.5% | CONCERN | 14.4% → 26.5%. Steady decline. Find top 3 error types and address specifically.
Juans | 9.5% | 21.2% | CONCERN | 9.5% → 21.2%. Moved past 20% threshold. Weekly review needed until under 12%.
Chauncey_w | 14.1% | 24.8% | CONCERN | 14.1% → 24.8%. Continuing multi-year decline. Reset performance expectations formally.
Raul | 8.8% | 18.8% | CONCERN | 8.8% → 18.8%. Doubled on high volume. Coaching needed.
Elenam | 9.4% | 18.2% | CONCERN | 9.4% → 18.2%. Doubled. High volume increase (106 → 231 jobs) may be causing rush errors.
Ricardot | 7.4% | 15.1% | WATCH | Schedule review and find root cause.
Rose | 2.9% | 9.2% | WATCH | Schedule review and find root cause.
Davidy | 0.0% | 5.9% | WATCH | Schedule review and find root cause.
Jonp | 11.6% | 14.8% | WATCH | Schedule review and find root cause.
CREW MEMBERS — IMPROVING OR HOLDING STRONG
Crew | 2025 GB% | 2026 GB% | Status | Note
Ray | 4.7% | 7.7% | SLIGHT SLIP | Small uptick (4.7% → 7.7%) but still well within target. Monitor but no action needed.
Anthonya | 2.6% | 2.7% | STABLE → | Near-perfect hold: 2.6% → 2.7%. STAR crew year over year. High trust assignments.
Joseph | 2.5% | 1.8% | STABLE → | Steady excellence: 2.5% → 1.8%. Consistent high quality. Assign to training role.
Diegor | 5.8% | 4.6% | STABLE → | Slight improvement: 5.8% → 4.6%. High volume + low errors. Promote to lead crew.
Johnv | 10.7% | 3.4% | IMPROVED ↑ | Biggest improvement: 10.7% → 3.4%. From concern to STAR. Find out what changed and share with team.
DRAFTERS — WHO IMPROVED AND WHO DECLINED
Drafter | 2025 GB% | 2026 GB% | Status | Action
Oleg | 5.9% | 23.2% | CRITICAL ↓↓ | URGENT: Review every Oleg draft this week. Go-backs quadrupled. Must find root cause — equipment, process, or workload pressure.
Caitlyn | 22.2% | 70.6% | CRISIS ↓↓↓ | IMMEDIATE: Stop all new Caitlyn assignments. 70.6% go-back is not acceptable. Senior must review and approve every draft until resolved.
Glenn | 18.1% | 16.7% | STABLE → | Slight improvement but still above 10% target. Weekly coaching is working — continue.
Jon_w | 50.0% | 43.2% | WATCH | 2025 data too small (2 drafts). 43.2% in 2026 is high. Needs senior sign-off gate before submission.